## MVP Overview
MVP Summary
AI-assisted property development concept platform - recommended first release.
KPI | Value | Notes | Formula / Source
Recommended MVP | Single Stand AI Concept Generator | Start with one real pilot use case, then expand to estate mode.
Total Min Hours | 295 | Sum of all feature minimums | Feature Estimate G5:G23
Total Max Hours | 506 | Sum of all feature maximums | Feature Estimate H5:H23
Total Avg Hours | 401 | Average planning estimate | Feature Estimate I5:I23
Suggested Team | 1 full-stack developer + 1 AI/full-stack support | Can be adjusted based on budget/speed.
Indicative Duration | 5-7 weeks after discovery | Depends on AI/layout complexity and feedback speed.
Phase 1 Boundary | Concept support only | Not final architectural, municipal, or QS certification.
Milestone | Scope | Output | Min Hours | Max Hours | Avg Hours | Duration
M1 Discovery | Scope lock, field mapping, wireframes | Approved MVP scope + build roadmap | 23 | 40 | 32 | 2-3 days
M2 Base Platform | Auth, project dashboard, data room, database | Working project workspace | 40 | 62 | 51 | 1-1.5 weeks
M3 AI Intelligence | Document extraction, document Q&A, brief builder | AI summaries + structured project brief | 56 | 92 | 74 | 1-1.5 weeks
M4 Concepts & Cost | Site input, buildable envelope, layout concepts, style direction, cost range | 2-3 concept options + costing | 120 | 210 | 165 | 2-3 weeks
M5 Export & QA | PDF export, deployment, QA, feedback fixes | Live MVP + concept report | 44 | 80 | 62 | 1 week

## Feature Estimate
AI Property Development MVP - Feature & Hour Estimate
Client-facing estimate. Planning ranges only; final quote should follow discovery.
Area | Feature | Description | Priority | Phase | Deliverable | Min Hours | Max Hours | Avg Hours | Notes
Discovery | MVP scope lock | Review current AI Studio app, confirm pilot use case, and decide what Phase 1 must prove. | Must have | M1 Discovery | Approved MVP scope + roadmap | 8 | 14 | 11 | Best first paid milestone before full development.
Discovery | Field mapping | Define project, stand, document, and brief fields needed for the MVP. | Must have | M1 Discovery | Field checklist | 5 | 8 | 7 | Prevents missed requirements later.
UX/UI | MVP wireframes | Design simple screens for dashboard, upload, brief builder, concept output, and reports. | Must have | M1 Discovery | Wireframe view | 10 | 18 | 14 | Lightweight, not overdesigned.
Platform | Authentication & user setup | Secure login and basic workspace access. | Must have | M2 Base Platform | User accounts | 8 | 12 | 10 | Supabase or Clerk recommended.
Platform | Project dashboard | Create and manage property projects with status, summary, modules, and outputs. | Must have | M2 Base Platform | Project workspace | 16 | 26 | 21 | Foundation for all future modules.
Platform | Data room / file uploads | Upload and organise PDFs, images, site plans, zoning docs, reports, and supporting files. | Must have | M2 Base Platform | Document library | 16 | 24 | 20 | Object storage + metadata in database.
AI | Document extraction | Extract structured info from documents: property facts, rules, constraints, risks, and decisions. | Must have | M3 AI Intelligence | AI summary + structured fields | 24 | 38 | 31 | Use LLM extraction + JSON schemas.
AI | Project document chat | Ask questions against uploaded project documents. | Should have | M3 AI Intelligence | Project assistant | 14 | 24 | 19 | Optional if budget is tight.
Product | Structured brief builder | Guided form for bedrooms, bathrooms, floors, style, garage, patio/braai, priorities, and budget level. | Must have | M3 AI Intelligence | Validated house/project brief | 18 | 30 | 24 | Critical for reliable concept output.
Site | Stand/site input module | Capture location, stand size, road/access side, orientation, contour notes, constraints, and manual site assumptions. | Must have | M4 Concepts & Cost | Site profile | 18 | 30 | 24 | Manual-first input is safest for MVP.
Site | Buildable envelope v1 | Create simple constraint summary and visual placement assumptions from zoning/rules and user inputs. | Must have | M4 Concepts & Cost | Buildable-zone summary | 18 | 32 | 25 | Advanced geospatial automation later.
AI | Concept generation workflow | Generate 2-3 early layout strategies with rationale, pros/cons, and scoring. | Must have | M4 Concepts & Cost | Concept option cards | 30 | 50 | 40 | Core MVP differentiator.
Design | Schematic layout output | Show basic site/floor-plan concepts using SVG/canvas diagrams, labels, driveway, patio, and room zones. | Must have | M4 Concepts & Cost | Visual concept diagrams | 24 | 44 | 34 | Not full CAD drawings in MVP.
Design | Exterior style direction | Generate basic visual style direction, material notes, and render prompt packages. | Should have | M4 Concepts & Cost | Style/renders section | 12 | 24 | 18 | Optional for first launch.
Cost | Rough cost estimator | Estimate range using floor area, quality level, complexity factors, external works, and contingency. | Must have | M4 Concepts & Cost | Cost range + assumptions | 18 | 30 | 24 | Not final QS pricing.
Reports | PDF concept pack | Export project summary, brief, constraints, concept options, recommendation, and costing into a clean PDF. | Must have | M5 Export & QA | Downloadable report | 18 | 32 | 25 | Main shareable output.
Delivery | Deployment | Deploy MVP, configure environment, storage, database, and production settings. | Must have | M5 Export & QA | Live MVP | 10 | 18 | 14 | Vercel + managed database recommended.
Delivery | QA & feedback round | Test workflows, fix core issues, and apply one feedback pass after review. | Must have | M5 Export & QA | Stabilised MVP | 16 | 30 | 23 | Keeps first launch reliable.
Delivery | Project management & communication | Planning, check-ins, scope coordination, and delivery management. | Must have | All | Smooth delivery | 12 | 22 | 17 | Can be folded into milestones.

## Milestones
Milestone Plan
Suggested delivery split after discovery approval.
Milestone | Scope | Main Deliverable | Min Hours | Max Hours | Avg Hours | Indicative Duration
M1 Discovery | Scope lock, field mapping, wireframes | Approved MVP scope + build roadmap | 23 | 40 | 32 | 2-3 days
M2 Base Platform | Auth, project dashboard, data room, database | Working project workspace | 40 | 62 | 51 | 1-1.5 weeks
M3 AI Intelligence | Document extraction, document Q&A, brief builder | AI summaries + structured project brief | 56 | 92 | 74 | 1-1.5 weeks
M4 Concepts & Cost | Site input, buildable envelope, layout concepts, style direction, cost range | 2-3 concept options + costing | 120 | 210 | 165 | 2-3 weeks
M5 Export & QA | PDF export, deployment, QA, feedback fixes | Live MVP + concept report | 44 | 80 | 62 | 1 week
Cross-phase effort | Project management & communication | Included in the total estimate separately as cross-phase effort.

## Assumptions
Assumptions & Scope Boundaries
Use this to keep the MVP conversation safe and clear.
Category | Included in MVP | Held for Later
Architecture / layouts | Early-stage schematic site/floor-plan concepts, logic, scores, and rationale. | Final architectural drawings, structural design, municipal-ready packages, CAD/BIM automation.
Site/geospatial | Manual-first stand/site inputs with uploaded documents and basic visual assumptions. | Fully automated survey/CAD/KML parsing, terrain mesh generation, advanced GIS layers.
Document intelligence | AI summary, extracted constraints, zoning/rules notes, project facts, document Q&A. | Legal certification, guaranteed compliance decisions, automatic municipal approvals.
Costing | Rough cost range using formula-based assumptions and complexity multipliers. | Final QS BOQ, supplier pricing, procurement, or guaranteed construction budget.
Visuals | Concept visuals, material/style direction, optional render prompt workflow. | Photorealistic final marketing renders or detailed 3D architectural model.
Estate mode | Pilot can support one stand/spec-house use case. | Full estate masterplan mode, stand categorisation, repeatable house-type optimisation.
Client inputs | One pilot project/stand, available documents, desired output format, feedback on generated concepts. | The team cannot infer missing legal/survey details without client-provided material.